Technology & Infrastructure Enablers for Africa

PECH GROUP HOLDINGS LTD

## Table of Contents

- Executive Summary

- The Opportunity

- PECH Ecosystem Overview

- Ecosystem Architecture Diagram

- Platform Breakdown & Build Strategy

- Phased Execution Roadmap (24 Months)

- Capital Deployment Plan

- Human Capital & Hiring Plan

- Technology & AI Tools Budget

- Hardware & Device Strategy

- Licensing, Compliance & Regulatory

- Marketing & Customer Acquisition

- Revenue Model & Financial Projections

- Risk Analysis & Mitigation

- Equity & Governance

- Key Performance Indicators

- Use of Funds Summary

- Appendix

## 1. Executive Summary

PECH Group Holdings Ltd is building Africa’s first vertically-integrated Commerce & Infrastructure Operating System — a multi-platform ecosystem combining:

- Embedded ERP — Free business management software for African SMEs

- IoT & Smart Systems Platform — Hardware + cloud for energy, security, estate management

- Smart Water Controllers — Multi-tier water level controllers (Basic → IoT → Industrial/SCADA)

- Smart Home & Electrical — Switches, sockets, cameras (smart and non-smart), energy storage

- Learning Tablets & EdTech — Hardware for education content deployment with open API for creators

- Yiwu-Style Marketplace — Digital twin of Nigeria’s physical wholesale markets

- Spoke-and-Hub Logistics — Cainiao-inspired parcel management platform

- Payments Infrastructure — PSSP/PTSP-licensed payment processing across all platforms

- AI Platform Services — Self-hosted LLMs (Qwen2.5), RAG chatbots, Vision AI, OCR, TTS/STT, accounting AI

- Advertising & LED Displays — Digital signage and advertising infrastructure (Phase 2)

- Self-Service Kiosks — Multi-purpose payment and information kiosks

### Our Mission

PECH is a technology and infrastructure enabler for people. We build the digital backbone that African businesses, homes, and communities run on. Every product we ship — from a ₦1,500 premium socket to a ₦350,000 estate system — represents reliability, quality, and good price for your money. We sell high-end products AND equally good affordable products, but never bad products. Quality is our brand promise.

### Designed for Africa, Powered by PECH

All PECH products are designed specifically for African conditions — wide voltage tolerance (140–280V), heat resistance, dust/water protection, and offline capability. Every product is progressively integrated across PECH’s entire ecosystem: the IoT platform powers device intelligence, the ERP connects business operations, the Marketplace enables discovery and sales, Logistics handles delivery, and Payments processes transactions. A PECH smart switch is not just a switch — it’s a node in Africa’s commerce and infrastructure operating system.

This plan details the deployment of ₦250,000,000 in secured capital across the first 24 months of simultaneous lean platform launches, targeting Nigeria first with a clear path to West African expansion. After Month 9, as the business gains traction through hardware sales and software product revenue, additional capital will be deployed to secure the PSSP license and accelerate growth.

### Why PECH Will Win

| Competitive Edge | Description |
| --- | --- |
| Ecosystem Lock-In | Free ERP creates daily dependency; hardware deepens it |
| AI-Native Platform | Self-hosted LLMs, RAG chatbots, Vision AI, OCR — all open-source (Apache-2.0/MIT) |
| African-Optimized | Offline-first, power-resilient, multi-network design |
| Data Moat | Transaction + energy + logistics data enables credit scoring + AI training |
| Founder Advantage | Founder directly sources hardware from China (Shenzhen) |
| No Single-Point Competition | No African company combines all 6 layers + AI |

### Key Targets (24 Months)

| Metric | Target |
| --- | --- |
| Active Merchants (ERP) | 3,000–5,000 |
| IoT Devices Deployed | 800–1,500 |
| Markets Digitized | 5–8 major markets |
| Monthly Recurring Revenue | ₦15M–₦25M by Month 24 |
| Team Size | 30–37 people |
| Payment Volume (GMV) | ₦1B+ cumulative |
| PSSP License | Obtained (Month 9+) |

## 2. The Opportunity

### Africa’s Commerce Infrastructure Gap

| Problem | Scale |
| --- | --- |
| African SMEs without ERP/digital tools | 90%+ |
| Nigerian businesses using informal credit | 80%+ |
| African IoT market (2026) | $4.85 Billion |
| Nigeria food waste from cold chain failure | $2.3–3.3 Billion/year |
| Nigerian merchants on WhatsApp-only sales | 70%+ |
| Markets with zero digital presence | Thousands |

### Why Now

- Smartphone penetration accelerating across Nigeria

- Digital payments adoption (Paystack, Flutterwave, OPay growing rapidly)

- CBN pushing financial inclusion and PSSP licensing

- No dominant African commerce OS exists yet — first-mover advantage is real

- Nigeria’s Data Protection Act (NDPA) favors local platforms

## 3. PECH Ecosystem Overview

PECH Commerce OS Architecture

PECH is modeled after Alibaba Group’s layered architecture, adapted for African realities:

| PECH Layer | Alibaba Equivalent | Function |
| --- | --- | --- |
| Embedded ERP | Alibaba Merchant Tools / DingTalk | Free business software → creates daily dependency |
| YiwuGou Marketplace | 1688.com / YiwuGou | Digital twin of physical markets → national discovery |
| Payments & Wallets | Alipay / Ant Group | Payment processing → data visibility |
| Logistics Platform | Cainiao Network | Spoke-and-hub parcel management → movement coordination |
| Fintech & Credit | Ant Financial / MYbank | Credit scoring from real data → monetization |
| Data & APIs | Alibaba Cloud / Data Services | Trade intelligence → sold to banks/governments |
| IoT & Smart Systems | Alibaba Cloud IoT | Energy, security, estate management → infrastructure |
| Smart Hardware | Ant POS / Alibaba Devices | POS, meters, controllers → hardware monetization |

## 4. Ecosystem Architecture Diagram

┌─────────────────────────────────────────────────────────────────────────┐
│                    PECH GROUP HOLDINGS LTD                              │
│              Africa's Commerce & Infrastructure OS                      │
├─────────────────────────────────────────────────────────────────────────┤
│                                                                         │
│  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐  ┌────────────┐  │
│  │   EMBEDDED   │  │  MARKETPLACE │  │  SPOKE & HUB │  │  IoT &     │  │
│  │     ERP      │  │  (YiwuGou)   │  │  LOGISTICS   │  │  SMART     │  │
│  │              │  │              │  │              │  │  SYSTEMS   │  │
│  │ • Inventory  │  │ • Market     │  │ • Spoke App  │  │            │  │
│  │ • Sales      │  │   Digitize   │  │   (52 scrns) │  │ • Energy   │  │
│  │ • Debtors    │  │ • Shop       │  │ • Hub App    │  │ • Security │  │
│  │ • Reporting  │  │   Directory  │  │   (94 scrns) │  │ • Estates  │  │
│  │ • Mobile-1st │  │ • Discovery  │  │ • Sorting    │  │ • Meters   │  │
│  └──────┬───────┘  └──────┬───────┘  └──────┬───────┘  └──────┬─────┘  │
│         │                 │                 │                 │         │
│  ┌──────┴─────────────────┴─────────────────┴─────────────────┴──────┐  │
│  │              PAYMENTS & FINANCIAL INFRASTRUCTURE                   │  │
│  │                                                                   │  │
│  │   ┌──────────┐  ┌──────────┐  ┌──────────┐  ┌──────────────┐    │  │
│  │   │  Wallet  │  │  Bank    │  │  Escrow  │  │  Smart POS   │    │  │
│  │   │  Ledger  │  │ Transfer │  │  (B2B)   │  │  Devices     │    │  │
│  │   └──────────┘  └──────────┘  └──────────┘  └──────────────┘    │  │
│  └──────────────────────────┬────────────────────────────────────────┘  │
│                             │                                           │
│  ┌──────────────────────────┴────────────────────────────────────────┐  │
│  │              DATA, AI & CREDIT SCORING ENGINE                     │  │
│  │                                                                   │  │
│  │  Transaction Data + Energy Usage + Payment History + Device       │  │
│  │  Uptime → Credit Score (0-100) → Banks / MFIs / Insurers        │  │
│  └──────────────────────────┬────────────────────────────────────────┘  │
│                             │                                           │
│  ┌──────────────────────────┴────────────────────────────────────────┐  │
│  │              OPEN API & DEVELOPER ECOSYSTEM                       │  │
│  │                                                                   │  │
│  │  REST APIs • Webhooks • SDKs (JS, Python, Flutter) • White-Label │  │
│  └───────────────────────────────────────────────────────────────────┘  │
│                                                                         │
│  ┌───────────────────────────────────────────────────────────────────┐  │
│  │              SMART HARDWARE LAYER                                 │  │
│  │                                                                   │  │
│  │  ┌─────────┐ ┌────────┐ ┌────────┐ ┌────────┐ ┌──────────────┐  │  │
│  │  │Smart POS│ │Tablets │ │IoT     │ │Smart   │ │Logistics     │  │  │
│  │  │Terminal │ │& Mini  │ │Control-│ │Meters  │ │Scanners &    │  │  │
│  │  │(ERP+Pay)│ │  PC    │ │  lers  │ │(Energy)│ │POS Devices   │  │  │
│  │  └─────────┘ └────────┘ └────────┘ └────────┘ └──────────────┘  │  │
│  └───────────────────────────────────────────────────────────────────┘  │
└─────────────────────────────────────────────────────────────────────────┘

### Technology Stack Architecture

┌─────────────────────────────────────────────────────┐
│                   DEVICE LAYER                       │
│  ESP32 • STM32 • Android POS • SUNMI Terminals      │
│  MQTT • HTTP • Modbus • LoRaWAN • NB-IoT            │
├─────────────────────────────────────────────────────┤
│                EDGE INTELLIGENCE                     │
│  Offline-first • Local rules • Data buffering        │
│  NanoMQ (MIT) • Node-RED (Apache 2.0)               │
├─────────────────────────────────────────────────────┤
│                  MESSAGING LAYER                     │
│  EMQX (Apache 2.0) • Apache Kafka • WebSockets      │
├─────────────────────────────────────────────────────┤
│                  CORE BACKEND                        │
│  Node.js / Go • PostgreSQL • TimescaleDB • Redis     │
│  ThingsBoard (Apache 2.0) • Keycloak (Auth)          │
├─────────────────────────────────────────────────────┤
│                   AI ENGINE (Self-Hosted)             │
│  Qwen2.5 LLM • Whisper STT • PaddleOCR • RT-DETR    │
│  Ollama/vLLM • LangChain • Qdrant • XGBoost • MLflow│
├─────────────────────────────────────────────────────┤
│               FRONTEND & MOBILE                      │
│  React (Web) • Flutter (Mobile) • Leaflet (Maps)     │
├─────────────────────────────────────────────────────┤
│              INFRASTRUCTURE & DEVOPS                 │
│  Docker • k3s (Kubernetes) • Apache APISIX • GitHub  │
│  Pech Cloud (Nigeria) • Self-Host Option             │
└─────────────────────────────────────────────────────┘

## 5. Platform Breakdown & Build Strategy

### 5.1 Embedded ERP Platform

| Aspect | Detail |
| --- | --- |
| Purpose | Free business management for SMEs |
| Target Users | Market traders, wholesalers, distributors |
| Core Modules | Inventory, Sales, Debtors/Creditors, Reporting |
| Build Strategy | Fork ERPNext (Apache 2.0) → Simplify → Mobile-first → Embed payments |
| Key Differentiator | Works offline, Nigerian market-optimized, integrated with payments |
| Revenue Model | FREE (monetize via hardware + payments + data) |

### 5.2 YiwuGou-Style Marketplace

| Aspect | Detail |
| --- | --- |
| Purpose | Digital twin of Nigeria’s physical markets |
| Target Users | Buyers searching wholesale goods nationally |
| Core Features | Market → Section → Shop Directory, Verified listings, WhatsApp contact |
| Build Strategy | Custom build (React + Flutter + PostgreSQL) |
| Pilot Markets | Alaba (Lagos), Ariaria (Aba), Sabon Gari (Kano) |
| Revenue Model | Featured listings, premium visibility, data services |

### 5.3 Spoke-and-Hub Logistics Platform

| Aspect | Detail |
| --- | --- |
| Purpose | Parcel pickup station & hub management (Cainiao model) |
| Target Users | Station operators, hub managers, couriers |
| Core Features | Package check-in/out (52 screens), Hub management (94 screens, 355+ features), Tracking, Sorting |
| Build Strategy | Custom build from complete documentation spec |
| Hardware | SUNMI POS terminals, barcode scanners, sorting machines |
| Revenue Model | Per-package fees, station licensing, premium features |

### 5.4 IoT & Smart Systems Platform

| Aspect | Detail |
| --- | --- |
| Purpose | Device management, energy monitoring, smart estates |
| Target Users | Solar installers, estate managers, commercial buildings |
| Core Features | Device provisioning, OTA updates, dashboards, AI analytics |
| Build Strategy | Fork ThingsBoard (Apache 2.0) → Customize → Brand as Pech Cloud |
| Priority Verticals | Energy monitoring, Surveillance, Estate billing |
| Revenue Model | Hardware margin (30-40%) + SaaS (₦1,500-₦7,500/device/month) |

### 5.5 Payments Infrastructure

| Aspect | Detail |
| --- | --- |
| Purpose | Process payments across ALL PECH platforms |
| Strategy Phase 1 | Partner with Paystack/Flutterwave for payments + partner PTSP for POS terminals + partner bank for settlement (Month 1–9) |
| Strategy Phase 2 | Obtain PSSP license from CBN — own payment gateway processing (Month 9+, after business traction from hardware sales + software revenue) |
| Strategy Phase 3 | Add PTSP license for own POS terminal operations (when justified by volume) |
| Corporate Structure | PECH Group Holdings (parent) → PECH Payments Ltd (subsidiary, holds PSSP) → future subsidiaries for PTSP/PSS |
| Revenue Model | Transaction fees (0.5-1.5% per transaction) |

### 5.6 Smart Water Controllers

| Aspect | Detail |
| --- | --- |
| Purpose | Multi-tier smart water level controllers for African conditions |
| Target Users | Households, estates, hotels, hospitals, industrial boreholes |
| Tier 1 — Basic | Float switches + Arduino Nano, auto pump control, dry-run protection, LED/buzzer (₦22K–₦30K) |
| Tier 2 — Mid-Range | Ultrasonic sensor + ESP8266, LCD display, WiFi monitoring, dual-tank support (₦45K–₦60K) |
| Tier 3 — Smart IoT | ESP32 + SIM800L GSM, mobile app, SMS/USSD alerts, OTA firmware, energy tracking, anti-cycling (₦72K–₦95K) |
| Tier 4 — Industrial/SCADA | STM32 + SIM7600 4G, RS485/Modbus, LoRa, 3-phase, redundant sensors, DIN-rail (₦175K–₦250K) |
| ODM Strategy | Full design ownership, editable source files, NDA with Chinese ODMs, EVT→DVT→PVT validation |
| Key Safety | 140–280VAC tolerance, MOV+TVS protection, hardwired dry-run interlock, conformal coating, IP65+ |
| Revenue Model | Hardware margin (40-60%) + IoT SaaS for Tier 3-4 |

### 5.7 Smart Home & Electrical Products

| Aspect | Detail |
| --- | --- |
| Purpose | Smart and non-smart electrical products for homes and businesses |
| Product Lines | Smart switches, smart sockets, smart cameras, IP cameras, non-smart switches/sockets |
| Phase 1 Products | Smart switches, smart sockets, WiFi cameras, basic switches/sockets |
| Integration | All smart products connect to PECH IoT platform, controlled via app |
| Quality Standard | High-end AND affordable options — no bad products — reliability is the brand |
| Revenue Model | Hardware margin (35-50%) + SaaS for camera/monitoring subscriptions |

### 5.8 Learning Tablets & EdTech Platform

| Aspect | Detail |
| --- | --- |
| Purpose | Deploy educational content via PECH-branded tablets |
| Phase 1 Strategy | Source Android learning tablets from China; sell as-is with pre-loaded content |
| Phase 2+ Strategy | Control the firmware and software; build content delivery platform |
| Content Model | Partner with content creators; provide open API for integration to PECH devices |
| API Strategy | Content creators get REST API + SDKs to deploy their content to PECH tablet fleet |
| Target Users | Schools, parents, tutoring centers, corporate training |
| Revenue Model | Hardware margin + content creator revenue share (30/70 split) + institution licensing |

### 5.9 Energy Storage Systems

| Aspect | Detail |
| --- | --- |
| Purpose | Battery backup systems for IoT devices and home/business power |
| Products | Mini UPS for IoT, LiFePO4 home batteries, solar battery systems |
| Integration | Monitored via PECH IoT platform, smart charging, remote diagnostics |
| Target Users | IoT installations, homes, small businesses, solar setups |
| Revenue Model | Hardware margin (30-40%) + monitoring SaaS |

### 5.10 Advertising & LED Displays (Phase 2)

| Aspect | Detail |
| --- | --- |
| Purpose | Digital signage and advertising infrastructure in markets and public spaces |
| Phase 2 Launch | Start with LED display hardware sourcing + advertising management platform |
| Products | Indoor/outdoor LED screens, digital menu boards, market advertising panels |
| Integration | Content managed via PECH platform, remote update, scheduling |
| Revenue Model | Hardware sales + advertising revenue share + display-as-a-service |

## 6. Phased Execution Roadmap (24 Months)

24-Month Phased Roadmap

### Phase 1: Foundation (Months 0–3) — “Build the Engine”

| Activity | Deliverable |
| --- | --- |
| Core team hiring (5-7 people) | Architecture locked, team operational |
| ERP MVP development | Basic inventory + sales + mobile app |
| IoT platform setup | ThingsBoard fork + Pech branding |
| Hardware sourcing (China) | First batch POS + IoT devices ordered |
| Company registration & compliance | CAC, NCC engagement, legal setup |
| Marketplace design | UI/UX complete, backend started |
| Logistics app design finalization | Spoke App development started |

Budget Allocation: ₦55,000,000

### Phase 2: MVP & Pilot (Months 4–6) — “First Contact with Market”

| Activity | Deliverable |
| --- | --- |
| ERP pilot (50 merchants) | Live in 1 market (Alaba, Lagos) |
| IoT pilot (30 devices) | 3 solar installer partnerships |
| Marketplace alpha | 1 market digitized (500 shops) |
| Spoke App alpha | 2 pickup station pilots |
| Hardware delivery (China → Nigeria) | 100 POS + 50 IoT devices |
| Payment integration (Paystack) | Live transactions |
| Field agent recruitment | 10 agents deployed |

Budget Allocation: ₦52,000,000

### Phase 3: Market Entry (Months 7–9) — “Prove the Model”

| Activity | Deliverable |
| --- | --- |
| ERP expansion (500 merchants) | 2 additional markets |
| IoT commercial launch | Energy vertical live |
| Marketplace expansion | 3 markets, 1,500 shops |
| Logistics platform beta | 5 spoke stations operational |
| PSSP license application filed | CBN engagement started |
| Marketing campaigns | Lagos + Abuja |
| Support team scaled | 3 support reps |

Budget Allocation: ₦55,000,000

### Phase 4: Scale & Revenue (Months 10–12) — “Revenue Engine On”

| Activity | Deliverable |
| --- | --- |
| ERP at 1,500 merchants | Daily active usage proven |
| IoT at 300 devices | SaaS revenue flowing |
| Marketplace at 3,000 shops | Featured listings revenue |
| Logistics at 10 stations | Package volume growing |
| Payments processing ₦100M+/month | Transaction fee revenue |
| Data analytics dashboard | Credit scoring prototype |
| Second hardware batch | 200 POS + 100 IoT devices |

Budget Allocation: ₦45,000,000

### Phase 5: Ecosystem Maturity (Months 13–18) — “Lock-In & Monetize”

| Activity | Deliverable |
| --- | --- |
| ERP at 3,000 merchants | Market dependency established |
| IoT at 800 devices | Multi-vertical (energy + estates) |
| Marketplace at 5+ markets | National visibility |
| PSSP license operational | Own payment processing via PECH Payments Ltd (subsidiary) |
| Developer API launched | SDK + webhooks live |
| Credit scoring pilot | 2 MFI partnerships |
| Installer certification program | 20 certified installers |
| Third hardware batch + new SKUs | Smart meters, tablets |

Budget Allocation: ₦35,000,000

### Phase 6: Growth & Expansion (Months 19–24) — “Scale & Consolidate”

| Activity | Deliverable |
| --- | --- |
| ERP at 5,000 merchants | Multi-city presence established |
| IoT at 1,500 devices | Revenue from SaaS subscriptions growing |
| Marketplace at 8+ markets | National brand recognition |
| Payment volume ₦500M+/month | Transaction fee revenue significant |
| PTSP license evaluation | Assess justification for own POS terminal license |
| Fourth hardware batch | Expanded product line, higher volume |
| West Africa research | Ghana/Kenya assessment complete |
| Revenue approaching self-sustainability | Operating costs largely covered by revenue |

Budget Allocation: ₦10,000,000 (operational costs increasingly covered by revenue)

## 7. Capital Deployment Plan

### 7.1 Total Budget Allocation (₦250,000,000 / 24 Months)

| Category | Amount (₦) | % of Total |
| --- | --- | --- |
| Hardware Procurement (China Sourcing — 25 SKUs) | ₦75,000,000 | 30.0% |
| Human Capital (Salaries & Contractors) | ₦70,000,000 | 28.0% |
| Technology Infrastructure & AI Tools | ₦28,000,000 | 11.2% |
| Office, Equipment & Operations | ₦20,000,000 | 8.0% |
| Contingency & Emergency Reserve (FX + unforeseen) | ₦18,000,000 | 7.2% |
| Marketing & Customer Acquisition | ₦15,000,000 | 6.0% |
| Logistics Platform (Stations Setup) | ₦12,000,000 | 4.8% |
| Licensing, Legal & Compliance | ₦12,000,000 | 4.8% |
| TOTAL | ₦250,000,000 | 100% |

PSSP LICENSE CAPITAL (After Month 9 — from business traction): - After Month 9, revenue from hardware sales and software products justifies deploying additional capital for PSSP licensing - PSSP License: ~₦205M (₦100M share capital + ₦100M escrow + fees + PCI DSS) — held by PECH Payments Ltd (subsidiary) - Payment processing in Phase 1 (Months 1–9) uses licensed PSP partners (Paystack/Flutterwave) + partner PTSP for POS terminals + partner bank for settlement - PTSP license pursued later when own POS terminal volume justifies the ~₦201M capital requirement

### 7.2 Monthly Cash Flow Projection

| Quarter | Months | Monthly Burn (₦) | Cumulative Spend (₦) | Revenue (₦) |
| --- | --- | --- | --- | --- |
| Q1 | 1–3 | ₦12.0M | ₦36.0M | ₦0 |
| Q2 | 4–6 | ₦14.0M | ₦78.0M | ₦1.5M |
| Q3 | 7–9 | ₦14.5M | ₦121.5M | ₦8.0M |
| Q4 | 10–12 | ₦13.0M | ₦160.5M | ₦22.0M |
| Q5 | 13–15 | ₦11.0M | ₦193.5M | ₦32.0M |
| Q6 | 16–18 | ₦9.5M | ₦222.0M | ₦42.0M |
| Q7 | 19–21 | ₦7.0M | ₦243.0M | ₦50.0M |
| Q8 | 22–24 | ₦2.3M | ₦250.0M | ₦58.0M |

Break-even projected: Month 16–18 (operational break-even) Cash-positive: Month 19+ (revenue exceeds burn rate)

Budget Allocation

### 7.3 Budget Allocation Visual

Hardware (25 SKUs)██████████████████████████████░░  30.0%  ₦75M
  Human Capital     ████████████████████████████░░░░  28.0%  ₦70M
  Tech & AI Tools   ███████████░░░░░░░░░░░░░░░░░░░░  11.2%  ₦28M
  Office & Ops      ████████░░░░░░░░░░░░░░░░░░░░░░░   8.0%  ₦20M
  Contingency/FX    ███████░░░░░░░░░░░░░░░░░░░░░░░░   7.2%  ₦18M
  Marketing         ██████░░░░░░░░░░░░░░░░░░░░░░░░░   6.0%  ₦15M
  Logistics Setup   ████░░░░░░░░░░░░░░░░░░░░░░░░░░░   4.8%  ₦12M
  Legal/Compliance  ████░░░░░░░░░░░░░░░░░░░░░░░░░░░   4.8%  ₦12M

  * PSSP capital (~₦205M) deployed after Month 9 from business traction
  * PTSP capital (~₦201M) deployed later when justified by volume

## 8. Human Capital & Hiring Plan

Team Growth & Payroll

### 8.1 Phase-by-Phase Hiring

#### Phase 1 (Months 0–3): Foundation Team — 5 People

| # | Role | Monthly Salary (₦) | Equity | Why Now |
| --- | --- | --- | --- | --- |
| 1 | Founder/CEO (Hardware & Supply Chain) | ₦0 (Founder) | Majority | Vision + China sourcing |
| 2 | Founding Technical Architect (CTO) | ₦800,000 | 1–3% (4yr vest) | Architecture decisions are irreversible |
| 3 | Full-Stack Engineer #1 (ERP + Web) | ₦450,000 | — | ERP MVP delivery |
| 4 | Full-Stack Engineer #2 (Mobile) | ₦400,000 | — | Mobile-first requirement |
| 5 | Market Operations Manager | ₦300,000 | — | Market politics + onboarding |

Monthly payroll: ₦1,950,000 Quarterly payroll: ₦5,850,000

Compliance handled by legal consulting (₦1M/year). Accounting by external consultant (₦500K/year). UI/UX contracted per-project basis.

#### Phase 2 (Months 4–6): MVP & Pilot — 9 People

| # | Role | Monthly Salary (₦) | Notes |
| --- | --- | --- | --- |
| 6 | IoT/Embedded Engineer | ₦400,000 | Firmware + device integration + water controllers |
| 7 | DevOps Engineer | ₦350,000 | Cloud infrastructure + CI/CD |
| 8–9 | Field Agents (2 contract) | ₦80,000 each + per-merchant bonus | Merchant acquisition |

Monthly payroll: ₦3,060,000 Quarterly payroll: ₦9,180,000

#### Phase 3 (Months 7–9): Market Entry — 13 People

| # | Role | Monthly Salary (₦) | Notes |
| --- | --- | --- | --- |
| 10 | Payments Product Manager | ₦600,000 | Payment complexity management |
| 11 | Data Analyst | ₦350,000 | Credit scoring + insights |
| 12–13 | Support Representatives (2) | ₦150,000 each | Scale merchant support |

Monthly payroll: ₦4,310,000 Quarterly payroll: ₦12,930,000

#### Phase 4 (Months 10–12): Revenue Scale — 18 People

| # | Role | Monthly Salary (₦) | Notes |
| --- | --- | --- | --- |
| 14 | Logistics Operations Lead | ₦350,000 | Spoke-and-hub management |
| 15–16 | Junior Engineers (2) | ₦250,000 each | Scale development |
| 17–18 | Additional Field Agents (2) | ₦80,000 each | 2nd/3rd market |

Monthly payroll: ₦5,320,000 Quarterly payroll: ₦15,960,000

#### Phase 5 (Months 13–18): Ecosystem Maturity — 25-30 People

| # | Role | Monthly Salary (₦) | Notes |
| --- | --- | --- | --- |
| 19 | AI/ML Engineer | ₦600,000–₦1,000,000 | LLM deployment, RAG pipelines, fine-tuning |
| 20 | AI Data Engineer | ₦400,000–₦600,000 | Data pipelines, vector databases, embeddings |
| 21 | API/Platform Engineer | ₦450,000–₦700,000 | APISIX gateway, microservice architecture |
| 22 | Business Development Lead | ₦400,000 | Enterprise + partnerships |
| 23 | Technical Writer | ₦250,000–₦400,000 | API docs, user guides |
| 24 | Regional Field Coordinator | ₦150,000 | Abuja expansion |
| 25–28 | Additional Field Agents (4) | ₦80,000 each | National expansion |

Monthly payroll: ₦8,270,000–₦10,620,000 Phase 5 payroll (6 months): ₦49,620,000–₦63,720,000

#### Phase 6 (Months 19–24): Growth & Expansion — 30-37 People

| # | Role | Monthly Salary (₦) | Notes |
| --- | --- | --- | --- |
| 29 | MLOps Engineer | ₦500,000–₦800,000 | vLLM serving, model monitoring, scaling |
| 30 | AI Product Manager | ₦500,000–₦800,000 | AI feature roadmap across verticals |
| 31 | PSSP Compliance Officer | ₦400,000 | Regulatory compliance for payment license |
| 32 | Developer Advocate | ₦400,000–₦600,000 | API ecosystem, SDK support |
| 33 | Installer Training Manager | ₦350,000–₦500,000 | Installer certification, AI training |
| 34 | Fintech Ops/Agent Network Manager | ₦400,000–₦600,000 | Agent network, compliance |
| 35–36 | Additional Engineers (2) | ₦350,000 each | Scale payment platform |
| 37 | AI/ML Intern | ₦80,000–₦120,000 | Support AI team |

Monthly payroll: ₦11,250,000–₦14,590,000 Phase 6 payroll (6 months): ₦67,500,000–₦87,540,000

### 8.2 Total Human Capital Cost (24 Months)

| Phase | Duration | Avg Monthly (₦) | Total (₦) |
| --- | --- | --- | --- |
| Phase 1 | 3 months | ₦1,950,000 | ₦5,850,000 |
| Phase 2 | 3 months | ₦3,060,000 | ₦9,180,000 |
| Phase 3 | 3 months | ₦4,310,000 | ₦12,930,000 |
| Phase 4 | 3 months | ₦5,320,000 | ₦15,960,000 |
| Phase 5 | 6 months | ₦6,690,000 | ₦40,140,000 |
| Phase 6 | 6 months | ₦7,950,000 | ₦47,700,000 |
| TOTAL | 24 months |  | ₦131,760,000 |

Note: Actual budget is ₦70,000,000 for human capital. The difference is covered by: - Delayed hiring (Phase 5-6 roles shift based on revenue milestones) - Contract/per-project arrangements (UI/UX, compliance, field agents) - Revenue offsetting costs significantly from Month 10+ (projected ₦103M+ cumulative revenue by Month 18) - Phase 6 (Months 19-24) payroll largely self-funded by revenue — business is cash-positive by Month 19 - Performance-based bonuses replacing fixed salary increases - Lean team philosophy — hire only when revenue justifies it

Salary Validation (March 2026 Market Data): All salary figures benchmarked against Glassdoor, PayScale, and Levels.fyi Nigeria data: - CTO at ₦800K/mo is competitive (market range: ₦400K–₦1.4M) - Engineers at ₦400K–₦450K/mo are lean/startup-tier (market mid: ₦500K–₦800K), offset by equity - DevOps at ₦350K/mo is below market mid (₦250K–₦600K) — adjust after 6 months - Junior engineers at ₦250K/mo are reasonable for entry-level (market: ₦150K–₦300K) - Field agents at ₦80K + bonus is standard for contract agents - All salaries for on-site/local roles; remote international rates 3–5x higher

## 9. Technology & AI Tools Budget

### 9.1 Cloud Infrastructure

| Service | Monthly Cost (₦) | Annual (₦) | Notes |
| --- | --- | --- | --- |
| Cloud Hosting (AWS/Azure Nigeria) | ₦600,000 | ₦7,200,000 | Multi-service hosting |
| Database (PostgreSQL + TimescaleDB) | ₦150,000 | ₦1,800,000 | Managed instances |
| MQTT Broker (EMQX Cloud) | ₦100,000 | ₦1,200,000 | IoT messaging |
| CDN & Storage (S3-compatible) | ₦80,000 | ₦960,000 | Static assets + backups |
| Domain & SSL certificates | ₦20,000 | ₦240,000 | Multiple domains |

24-Month Infrastructure Total: ₦19,200,000

### 9.2 AI GPU Infrastructure (Self-Hosted)

PECH deploys self-hosted AI models on RTX 4090 GPU servers in Lagos, running open-source models only (Apache-2.0/MIT licenses) that can be rebranded and deployed without restriction.

| Item | Cost (₦) | Notes |
| --- | --- | --- |
| TRX50 AI Workstation — Phase 1 (RTX 4090 24GB, Threadripper 7960X, ASUS TRX50-SAGE, 128GB ECC RDIMM, 5TB NVMe, Seasonic TX-1600) | ₦8,200,000–₦11,000,000 | Landed Lagos from China (incl. 25-35% import duties + 7.5% VAT). Zero-waste platform — same box scales to Phase 3 |
| UPS (3kVA online) | ₦800,000–₦1,200,000 | Power backup for GPU server (sized for 2 GPUs) |
| Server Room AC (2HP inverter) | ₦650,000–₦1,000,000 | Cooling for 24/7 operation |
| Rack + Cabling + Network Switch | ₦300,000–₦600,000 | Server room setup (4U rackmount ready) |
| Dedicated Internet (100Mbps fiber) | ₦130,000–₦250,000/month | For model API serving |
| Cloud GPU (RunPod/Vast.ai) | ₦200,000–₦500,000/month | Burst capacity for large models |
| Total AI Infra (One-Time) | ₦9,950,000–₦13,800,000 |  |
| Total AI Infra (Monthly) | ₦330,000–₦750,000 | Internet + cloud GPU |
| Phase 2 Upgrade (add 2nd RTX 4090, +128GB RAM, +4TB NVMe) | ₦4,100,000–₦5,300,000 | Months 7-12; same workstation, just add components. Saves ₦4.4M-₦6.4M vs buying separate production server |

AI Models Deployed (All Open-Source, License-Safe): - Primary LLM: Qwen2.5-7B/14B (Apache-2.0) — chatbots, RAG, content generation - Code: Qwen2.5-Coder (Apache-2.0) — developer tools, code review - Speech-to-Text: Whisper (MIT) — voice commands, transcription - Text-to-Speech: Piper TTS (MIT) — voice responses, accessibility - Vision: Qwen2-VL (Apache-2.0) — product image analysis, solar panel inspection - OCR: PaddleOCR (Apache-2.0) — invoice/receipt scanning, document digitization - Embeddings: MiniLM-L6 (MIT) — semantic search, RAG pipeline - Object Detection: RT-DETR (Apache-2.0) — defect detection, security cameras - ML: XGBoost (Apache-2.0), LightGBM (MIT) — fraud detection, credit scoring, pricing - Vector Database: Qdrant (Apache-2.0) — RAG knowledge store - Model Serving: Ollama (Phase 1) → vLLM (Phase 2/3)

See ai_strategy/PECH_AI_MODEL_CATALOG.md for full catalog of 50+ models.

### 9.3 AI & Development Tools

| Tool | Monthly Cost (₦) | Purpose |
| --- | --- | --- |
| GitHub Organization (Team) | ₦25,000 | Code hosting + CI/CD |
| Claude Pro / ChatGPT Team (5 seats) | ₦150,000 | AI-assisted development |
| Cursor IDE (5 seats) | ₦100,000 | AI pair programming |
| Figma (3 seats) | ₦45,000 | UI/UX design |
| Slack / Communication | ₦30,000 | Team coordination |
| Postman / API Tools | ₦20,000 | API testing |
| Sentry (Error monitoring) | ₦30,000 | Production monitoring |
| MLflow (Self-hosted) | ₦0 | ML experiment tracking |

Monthly AI/Tools: ₦400,000 24-Month Tools Total: ₦9,600,000

### 9.4 Total Technology Budget

| Category | 24-Month Total (₦) |
| --- | --- |
| Cloud Infrastructure | ₦18,400,000 |
| AI GPU Infrastructure — Phase 1 (one-time)* | ₦9,950,000–₦13,800,000 |
| AI GPU Infrastructure — Phase 2 upgrade (one-time)* | ₦4,100,000–₦5,300,000 |
| AI GPU Infrastructure (24mo recurring)* | ₦7,920,000–₦18,000,000 |
| AI & Development Tools | ₦9,600,000 |
| TOTAL (Cloud + Tools) | ₦28,000,000 |

*GPU infrastructure costs are budgeted under Hardware Procurement (₦75M) in Section 9.2, shown here for cross-reference only.

Note: The ₦28M technology budget prioritizes AI infrastructure via a zero-waste single-platform approach: the TRX50 Workstation bought in Phase 1 scales to Phase 3 by adding components (2nd GPU, RAM, storage) — never replacing the base system. This saves ₦4.4M-₦6.4M vs the old approach of buying a cheap starter server then replacing it with a production box. Cloud hosting costs are further reduced by self-hosting AI models and core databases on the same GPU server (PostgreSQL, Redis, Qdrant). Cloud GPU bursting is used only for fine-tuning and overflow capacity.

## 10. Hardware & Device Strategy

Hardware Product Portfolio — 25 SKUs

### 10.1 Hardware Product Line

Pricing Methodology: All unit costs below are fully-landed costs in Lagos, Nigeria. Calculated as: FOB price (sourced from Alibaba.com, 1688.com, Made-in-China.com wholesale listings, March 2026) × exchange rate (₦1,500/USD) × landed cost multiplier (1.50–1.60× depending on duty rate). The multiplier includes: CIF (FOB + 15% shipping), import duty (5–20%), surcharge (7% of duty), CISS (1% FOB), ETLS (0.5% CIF), VAT (7.5%), clearing (3%), local transport (2%), and amortized SONCAP certification costs.

#### Commerce & Business Devices

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-01 | Smart POS Terminal (Android, 4G, printer built-in) | $50 | ₦85,000 | ₦130,000 | 53% |
| SKU-02 | POS Tablet PC (10”, Android, LTE, for merchants) | $38 | ₦68,000 | ₦110,000 | 62% |
| SKU-03 | Self-Service Kiosk (Touch screen, payment, info) | $180 | ₦310,000 | ₦480,000 | 55% |
| SKU-04 | Receipt + Barcode Kit | $15 | ₦25,000 | ₦40,000 | 60% |
| SKU-05 | Logistics Scanner (SUNMI-compatible) | $22 | ₦38,000 | ₦60,000 | 58% |

#### IoT & Energy Devices

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-06 | IoT Energy Controller (ESP32, MQTT, solar) | $9 | ₦18,000 | ₦30,000 | 67% |
| SKU-07 | Smart Meter (energy monitoring, WiFi) | $16 | ₦30,000 | ₦48,000 | 60% |
| SKU-08 | Power Stability Kit (Mini UPS + surge) | $10 | ₦18,000 | ₦32,000 | 78% |
| SKU-09 | Energy Storage — Mini UPS (IoT backup, LiFePO4) | $20 | ₦38,000 | ₦60,000 | 58% |
| SKU-10 | Energy Storage — Home Battery (1kWh LiFePO4) | $85 | ₦155,000 | ₦240,000 | 55% |

#### Smart Water Controllers

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-11 | Water Controller Tier 1 (Basic — float switches, Arduino) | $5.50 | ₦12,000 | ₦22,000 | 83% |
| SKU-12 | Water Controller Tier 2 (Mid — ultrasonic, ESP8266, LCD) | $13 | ₦25,000 | ₦45,000 | 80% |
| SKU-13 | Water Controller Tier 3 (Smart IoT — ESP32, GSM, app) | $24 | ₦45,000 | ₦72,000 | 60% |
| SKU-14 | Water Controller Tier 4 (Industrial — STM32, 4G, SCADA) | $58 | ₦105,000 | ₦175,000 | 67% |

#### Smart Home & Electrical

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-15 | Smart Switch (WiFi, Tuya, 1-4 gang) | $3.50 | ₦7,000 | ₦12,500 | 79% |
| SKU-16 | Smart Socket (WiFi, energy monitoring) | $3.00 | ₦6,000 | ₦10,000 | 67% |
| SKU-17 | Smart Camera (WiFi, 1080p, night vision, 2-way audio) | $9 | ₦16,000 | ₦28,000 | 75% |
| SKU-18 | IP Camera (PoE, outdoor, 2K) | $20 | ₦36,000 | ₦58,000 | 61% |
| SKU-19 | Non-Smart Switch (Premium quality, 1-4 gang) | $0.90 | ₦1,800 | ₦3,500 | 94% |
| SKU-20 | Non-Smart Socket (Premium quality, 13A) | $0.70 | ₦1,400 | ₦2,800 | 100% |

#### Education & Display

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-21 | Learning Tablet (8”, Android, pre-loaded content) | $38 | ₦70,000 | ₦110,000 | 57% |
| SKU-22 | LED Display Panel (P3 indoor, 64×32cm) | $48 | ₦85,000 | ₦140,000 | 65% |
| SKU-23 | Outdoor LED Screen (P5, weatherproof, 96×48cm) | $90 | ₦160,000 | ₦250,000 | 56% |

#### Solar Products

| SKU | Device | FOB ($) | Landed Cost (₦) | Sell Price (₦) | Margin |
| --- | --- | --- | --- | --- | --- |
| SKU-24 | Solar Street Light (All-in-One, 60W LED, IP66, LiFePO4) | $55 | ₦132,000 | ₦200,000 | 52% |
| SKU-25 | Solar Rechargeable Fan (16”, DC, 3-speed, LED light, 6000mAh) | $16 | ₦36,000 | ₦45,000 | 25% |

### 10.2 Hardware Procurement Schedule

| Batch | Month | Devices | Total Landed Cost (₦) | Notes |
| --- | --- | --- | --- | --- |
| Batch 1 | Month 3 | 80 POS + 40 IoT + 20 Scanners + 50 Solar Fans | ₦12,200,000 | Pilot devices |
| Batch 2 | Month 7 | 150 POS + 80 IoT + 30 Water Controllers + 100 Smart Home + 30 Solar Lights | ₦18,400,000 | Market entry |
| Batch 3 | Month 12 | 200 POS + 150 IoT + 80 Water Controllers + 200 Smart Home + 50 Solar Lights + 100 Solar Fans | ₦24,800,000 | Scale batch |
| Batch 4 | Month 18 | Extended product line — higher volume | ₦15,100,000 | Growth batch (partially funded by revenue) |
| SONCAP Certification (amortized) | Various | — | ₦4,500,000 | ~₦1.5M/shipment for PC + SC + lab testing |
| TOTAL |  | ~1,360 devices | ₦75,000,000 |  |

Hardware Cost Validation — Sources (March 2026): - All FOB prices sourced from Alibaba.com, 1688.com, and Made-in-China.com wholesale listings - Exchange rate: ₦1,500/USD (CBN parallel market rate, March 2026) - Landed cost multiplier: 1.50× (10% duty items — solar, IoT) to 1.60× (20% duty items — electronics, fans) - Multiplier components: CIF (FOB+15%), duty (5–20%), surcharge (7% of duty), CISS (1% FOB), ETLS (0.5% CIF), VAT (7.5%), clearing (3%), local transport (2%) - SONCAP certification: $2,000–$13,000 per product category (SON.gov.ng schedules) - Shipping per 20ft container: $2,000–$4,000 (~₦3M–₦6M) - Solar street light prices verified against Inlux Solar 2026 price guide ($45–$120 range for 30W–200W) - Solar fan prices verified against Alibaba listings ($14–$26 range for 16” DC rechargeable models)

### 10.3 Solution Packages (What We Actually Sell)

#### Commerce Packages

| Package | Contents | Price (₦) | Target |
| --- | --- | --- | --- |
| Micro Trader Kit | Smart POS + Receipt Kit + Free ERP | ₦160,000 | Kiosks, small shops |
| SME Business Kit | Smart POS + Tablet + Barcode Scanner + Power Kit + ERP | ₦350,000 | Wholesalers |
| Market Power Seller Kit | 2× POS + Tablet + Full Kit + Priority Support | ₦500,000 | Large market shops |

#### IoT & Energy Packages

| Package | Contents | Price (₦) | Target |
| --- | --- | --- | --- |
| IoT Starter Kit | 3× Energy Controllers + Smart Meter + Dashboard | ₦140,000 | Solar installers |
| Estate Management Kit | 5× Smart Meters + CCTV + Access Control + Platform | ₦500,000 | Estate managers |
| Water Management Kit | Tier 3 Water Controller + Smart Meter + App Setup | ₦110,000 | Households, boreholes |
| Industrial Water Kit | Tier 4 Controller + Pressure Sensor + 4G + SCADA Dashboard | ₦250,000 | Hotels, hospitals, estates |

#### Smart Home Packages

| Package | Contents | Price (₦) | Target |
| --- | --- | --- | --- |
| Smart Home Starter | 4× Smart Switches + 2× Smart Sockets + App Setup | ₦70,000 | Homeowners |
| Home Security Kit | 2× Smart Cameras + Smart Switch + Cloud Storage | ₦75,000 | Families, landlords |
| Premium Home Kit | 8× Smart Switches + 4× Sockets + 2× Cameras + Energy Monitor | ₦200,000 | Premium homes |

#### Solar Products Packages

| Package | Contents | Price (₦) | Target |
| --- | --- | --- | --- |
| Solar Street Light Kit | Solar Street Light + Pole + Installation Guide | ₦230,000 | Estates, communities, LGAs |
| Solar Cooling Kit | 2× Solar Fans + Solar Panel | ₦100,000 | Homes, shops, market stalls |
| Community Solar Kit | 3× Solar Street Lights + 5× Solar Fans + Installation | ₦680,000 | Gated estates, rural communities |

#### Education & Display Packages

| Package | Contents | Price (₦) | Target |
| --- | --- | --- | --- |
| Learning Kit | Learning Tablet + Protective Case + 1 Year Content | ₦125,000 | Parents, schools |
| Classroom Kit | 10× Learning Tablets + Teacher Dashboard + Content License | ₦1,050,000 | Schools |
| Digital Signage Kit | LED Display + Media Player + PECH Ad Platform | ₦165,000 | Shops, markets |

## 11. Licensing, Compliance & Regulatory

Regulatory & Compliance Timeline

### 11.1 Corporate Structure

PECH Group Holdings Ltd (Parent — Technology Company)
├── PECH Payments Ltd (Subsidiary 1 — holds PSSP license)
├── PECH Terminal Services Ltd (Subsidiary 2 — holds PTSP license, later)
└── Future subsidiaries as needed

PECH Group Holdings Ltd is the parent technology company. Payment and terminal licenses are held by dedicated subsidiaries to isolate regulatory risk and meet CBN requirements for single-purpose entities.

### 11.2 Required Licenses & Approvals

| # | License/Approval | Authority | Cost (₦) | Timeline | Phase | From ₦250M? |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Company Registration (CAC — parent + subsidiary) | CAC | ₦100,000 | 2–4 weeks | Month 1 | Yes |
| 2 | Business Premises Permit | State Govt | ₦150,000 | 2–3 weeks | Month 1 | Yes |
| 3 | NCC Type Approval (IoT + Water Controllers) | NCC | ₦500,000 | 3–6 months | Month 1 | Yes |
| 4 | NDPA Compliance Registration + DPO | NDPC | ₦500,000 | 4–8 weeks | Month 2 | Yes |
| 5 | SONCAP (Hardware Import — PC + SC) | SON | ₦1,500,000/shipment | Per batch | Month 3 | Yes |
| 6 | Trademark Registration (1 class @ ₦100K) | Trademarks Registry | ₦100,000 | 6–12 months | Month 1 | Yes |
| 7 | NEMSA Compliance (Smart Meters + Water Controllers) | NEMSA | ₦350,000 | 2–4 months | Month 6 | Yes |
| 8 | Legal Consulting (₦1M/year × 2 years) | Law Firm | ₦2,000,000 | As needed | Ongoing | Yes |
| 9 | Accountant Consulting (₦500K/year × 2 years) | Accounting Firm | ₦1,000,000 | As needed | Ongoing | Yes |
| 10 | PSSP License Application | CBN | ₦1,100,000 | 6–12 months | Month 9+ | From business traction |
| 11 | PSSP Share Capital | CBN | ₦100,000,000 | With application | Month 9+ | From business traction |
| 12 | PSSP Escrow Deposit | CBN | ₦100,000,000 | With application | Month 9+ | From business traction |
| 13 | PCI DSS Certification | PCI SSC | ₦5,000,000 | 2–4 months | Month 10+ | From business traction |
| 14 | PTSP License (when justified) | CBN | ~₦201,000,000 | 6–12 months | When justified | When volume justifies |
| 15 | MMO License (for wallets & escrow) | CBN | ~₦4,001,000,000 | 10–13 months | When justified | Future — when justified |

### 11.3 PSSP, PTSP & MMO License — Detailed Breakdown

| Item | PSSP (Payments) | PTSP (POS Terminals) | MMO (Wallets & Escrow) |
| --- | --- | --- | --- |
| Application Fee | ₦100,000 | ₦100,000 | ₦100,000 |
| Licensing Fee | ₦1,000,000 | ₦1,000,000 | ₦1,000,000 |
| Minimum Share Capital | ₦100,000,000 | ₦100,000,000 | ₦2,000,000,000 |
| CBN Escrow Deposit | ₦100,000,000 (refundable) | ₦100,000,000 (refundable) | ₦2,000,000,000 (refundable) |
| PCI DSS Certification | ₦3,000,000–₦8,000,000 | Included with PSSP | Included with PSSP |
| Approval Process | AIP (2–3 mo) → Final (4–6 mo) | Same | AIP (6 mo) → Final (4–7 mo) |
| Total Capital Required | ~₦205,000,000 | ~₦201,000,000 | ~₦4,001,000,000 |
| What It Permits | Payment processing, gateway | POS terminal deployment | E-money issuance, wallets, customer escrow |

ESCROW DURATION: All CBN escrow deposits (PSSP, PTSP, MMO) are held for the entire duration of the license — as long as you operate under that license. CBN invests the escrow in treasury bills. Escrow is refundable only when you surrender the license. Annual license reviews assess performance targets.

COMBINED PSSP + PTSP CAPITAL: If pursuing both licenses, total capital requirement is approximately ₦400M+ (₦200M PSSP + ₦200M PTSP). A single entity may hold both with shared capital — requires CBN clarification.

MMO LICENSE (FOR WALLETS & ESCROW): A PSSP license alone does NOT permit holding customer funds or issuing digital wallets. To hold merchant escrow, operate business wallets, or issue e-money, an MMO license is required (₦2B capital + ₦2B escrow = ₦4B total). Until the ₦4B is justifiable, PECH will partner with an existing licensed MMO in a white-label arrangement to provide wallet services across all platforms.

### 11.4 Payment & Wallet License Strategy — Phased Approach

Phase 1: Partner Model (Months 1–9)

| Component | Provider | Capital from ₦250M |
| --- | --- | --- |
| Payment Gateway | Licensed PSP partner (Paystack/Flutterwave) | ₦0 |
| POS Infrastructure | Partner PTSP (e.g., Moniepoint, ITEX) | ₦0 |
| Wallet / Escrow | Partner Bank (white-label MMO) | ₦0 |
| Settlement | Partner Bank | ₦0 |
| Switching | Licensed Switch (e.g., Interswitch, NIBSS) | ₦0 |

Phase 2: Own PSSP (Month 9+ — from business traction)

After Month 9, revenue from hardware sales and software products justifies deploying capital for PSSP licensing through the subsidiary PECH Payments Ltd.

| License | Capital Required | Timeline |
| --- | --- | --- |
| PSSP (own payment gateway) | ~₦205M (₦100M capital + ₦100M escrow + fees + PCI DSS) | Month 9+ |

Phase 3: Strategic Growth (when justified)

| License | Capital Required | Timeline |
| --- | --- | --- |
| PTSP (own POS terminal network) | ~₦201M | When POS volume justifies |
| MMO (own wallets & escrow) | ~₦4B | When transaction volume justifies |

Key principle: PECH starts by partnering with already-licensed entities, builds revenue and track record, then progressively acquires its own licenses as the business justifies the capital. PSSP is the first priority — it enables PECH to control its own payment processing. PTSP and MMO follow only when volume justifies the capital requirement.

### 11.5 Total Compliance Budget (From ₦250M)

| Category | Amount (₦) | Notes |
| --- | --- | --- |
| Registration & Permits (CAC parent + subsidiary + Premises) | ₦250,000 | One-time |
| Device Certifications (NCC + NEMSA) | ₦850,000 | IoT devices + water controllers + meters |
| Data Protection (NDPA + DPO setup) | ₦500,000 | Annual CARs ongoing |
| Import Compliance (SONCAP × 3 shipments) | ₦4,500,000 | ~₦1.5M per shipment (PC + SC + lab testing) |
| Trademark Registration (1 class @ ₦100K) | ₦100,000 | Additional classes when justified |
| Legal Consulting (₦1M/year × 2 years) | ₦2,000,000 | As-needed regulatory counsel |
| Accountant Consulting (₦500K/year × 2 years) | ₦1,000,000 | Financial reporting + tax compliance |
| Other Registrations | ₦1,800,000 | Various state/federal permits |
| SUBTOTAL (From ₦250M Budget) | ₦11,000,000 |  |
| Buffer for unexpected compliance | ₦1,000,000 | NCC delays, additional certifications |
| TOTAL COMPLIANCE (From ₦250M) | ₦12,000,000 |  |
| DEPLOYED AFTER MONTH 9 (from business traction): |  |  |
| PSSP License + Capital + Escrow (via PECH Payments Ltd) | ₦205,000,000 | First priority |
| PCI DSS Certification | ₦5,000,000 | Required before own payment processing |
| DEPLOYED WHEN JUSTIFIED (future): |  |  |
| PTSP License + Capital + Escrow (via PECH Terminal Services Ltd) | ₦201,000,000 | When POS volume justifies |
| MMO License + Capital + Escrow | ₦4,001,000,000 | White-label MMO partnership until then |

## 12. Marketing & Customer Acquisition

Nigeria Market Entry Strategy

Customer Journey & Lock-In Flywheel

### 12.1 Marketing Strategy

| Phase | Strategy | Budget (₦) |
| --- | --- | --- |
| Months 1–3 | Brand identity, website, social media setup | ₦1,500,000 |
| Months 4–6 | Market association partnerships, demo units, pilot events | ₦2,500,000 |
| Months 7–9 | Digital marketing (Google, Meta, TikTok), installer workshops | ₦3,000,000 |
| Months 10–12 | Trade shows, enterprise sales collateral, case studies | ₦2,500,000 |
| Months 13–18 | National campaigns, developer hackathon, brand ambassadors | ₦3,000,000 |
| Months 19–24 | Expansion marketing, West Africa awareness, partnership events | ₦2,500,000 |
| TOTAL |  | ₦15,000,000 |

### 12.2 Customer Acquisition Cost Targets

| Channel | CAC Target (₦) | Lifetime Value (₦) | LTV:CAC Ratio |
| --- | --- | --- | --- |
| Field Agents (ERP merchants) | ₦5,000 | ₦120,000+ | 24:1 |
| Digital Marketing (Marketplace) | ₦2,000 | ₦50,000+ | 25:1 |
| Installer Partnerships (IoT) | ₦15,000 | ₦300,000+ | 20:1 |
| Logistics Station Onboarding | ₦25,000 | ₦500,000+ | 20:1 |

### 12.3 Market Entry Tactics (Nigeria-Specific)

| Tactic | Description | Cost |
| --- | --- | --- |
| Market Association MoUs | Partnership with Alaba, Ariaria, Sabon Gari leadership | ₦0 (relationship) |
| Demo Station Setup | Physical demo in 3 target markets | ₦1,500,000 |
| Installer Certification Program | Train 20 certified PECH installers | ₦1,000,000 |
| WhatsApp Business Integration | Leverage existing merchant behavior | ₦200,000 |
| Referral Bonus Program | ₦5,000 per successful merchant referral | Variable |

## 13. Revenue Model & Financial Projections

Revenue Streams Breakdown

### 13.1 Revenue Streams

| Stream | Source | Model | Monthly Target (Month 24) |
| --- | --- | --- | --- |
| Hardware Sales | POS, IoT devices, solar products, kits | One-time | ₦8,000,000 |
| Setup & Training | Installation fees | One-time | ₦1,200,000 |
| IoT SaaS | Device monitoring subscriptions | Recurring | ₦4,000,000 |
| Transaction Fees | Payment processing (0.5–1.5%) | Per-transaction | ₦5,000,000 |
| Marketplace | Featured listings, premium visibility | Recurring | ₦2,000,000 |
| Logistics | Per-package fees, station licensing | Per-transaction | ₦1,500,000 |
| Support Subscriptions | Premium support plans | Recurring | ₦800,000 |
| Solar Solutions | Street lights, fans, installation packages | One-time + Recurring | ₦2,500,000 |
| TOTAL MRR TARGET |  |  | ₦25,000,000 |

### 13.2 24-Month Revenue Projection

| Month | Hardware (₦M) | SaaS (₦M) | Transactions (₦M) | Solar (₦M) | Other (₦M) | Total (₦M) |
| --- | --- | --- | --- | --- | --- | --- |
| 1–3 | 0 | 0 | 0 | 0 | 0 | 0 |
| 4 | 0.5 | 0 | 0 | 0 | 0 | 0.5 |
| 5 | 0.8 | 0.1 | 0.1 | 0 | 0 | 1.0 |
| 6 | 1.0 | 0.2 | 0.2 | 0.1 | 0 | 1.5 |
| 7 | 1.5 | 0.4 | 0.5 | 0.3 | 0.2 | 2.9 |
| 8 | 2.0 | 0.6 | 0.8 | 0.5 | 0.3 | 4.2 |
| 9 | 2.5 | 0.8 | 1.0 | 0.6 | 0.4 | 5.3 |
| 10 | 3.0 | 1.2 | 1.5 | 0.8 | 0.5 | 7.0 |
| 11 | 3.5 | 1.5 | 2.0 | 1.0 | 0.6 | 8.6 |
| 12 | 4.0 | 1.8 | 2.5 | 1.2 | 0.7 | 10.2 |
| 13 | 4.5 | 2.0 | 2.8 | 1.3 | 0.8 | 11.4 |
| 14 | 5.0 | 2.2 | 3.0 | 1.5 | 0.9 | 12.6 |
| 15 | 5.5 | 2.5 | 3.2 | 1.6 | 1.0 | 13.8 |
| 16 | 5.5 | 2.8 | 3.5 | 1.8 | 1.0 | 14.6 |
| 17 | 6.0 | 3.0 | 3.8 | 2.0 | 1.2 | 16.0 |
| 18 | 6.0 | 3.2 | 4.0 | 2.0 | 1.2 | 16.4 |
| 19 | 6.5 | 3.5 | 4.2 | 2.2 | 1.3 | 17.7 |
| 20 | 7.0 | 3.8 | 4.5 | 2.3 | 1.4 | 19.0 |
| 21 | 7.0 | 4.0 | 4.8 | 2.5 | 1.5 | 19.8 |
| 22 | 7.5 | 4.0 | 5.0 | 2.5 | 1.5 | 20.5 |
| 23 | 8.0 | 4.0 | 5.0 | 2.5 | 1.8 | 21.3 |
| 24 | 8.0 | 4.0 | 5.0 | 2.5 | 1.8 | 21.3 |
| TOTAL | 95.3 | 43.6 | 56.4 | 25.2 | 18.1 | ₦243.6M |

Revenue vs Expenses

### 13.3 Path to Profitability

Revenue vs Expenses (₦ Millions per Month)

  Month:   1   3   6   9   12   15   18   21   24

  Revenue: 0   0  1.5  5.3  10.2 13.8 16.4 19.8 21.3
           ░░  ░░  █░  ███  ████ █████ ██████ ███████ ████████

  Expense: 12  12  14  14.5 13   11   9.5  7.0  2.3
           ██  ██  ███ ███  ███  ██░  █░░  █░░  ░░░░

  ✦ Break-even: Month 16–18 (operational break-even)
  ✦ Cash-positive: Month 19+ (revenue exceeds all costs)
  ✦ 24-Month Cumulative Revenue: ₦243.6M

## 14. Risk Analysis & Mitigation

Risk Assessment Heat Map

| # | Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Hardware import delays | High | Medium | Order 3 months ahead; dual suppliers in Shenzhen |
| 2 | PSSP license delay | High | Medium | Partner with Paystack/Flutterwave until approved |
| 3 | FX volatility (Naira/USD) | High | High | Pre-purchase hardware in bulk; hedge with USD reserves |
| 4 | Low merchant adoption | High | Medium | Free ERP + pilot incentives + market association partnerships |
| 5 | Power/internet instability | Medium | High | Offline-first design; power kits bundled; edge processing |
| 6 | Regulatory changes (NDPA/CBN) | Medium | Medium | Legal consulting; proactive compliance; data localization |
| 7 | Competitive entry (Tuya/global) | Medium | Low | Vertical specialization; African-optimized; installer loyalty |
| 8 | Cash burn exceeds plan | High | Medium | Conservative hiring; revenue milestones gate next phase |
| 9 | Key person departure (CTO) | High | Low | Equity vesting; knowledge documentation; pair programming |
| 10 | Security breach | High | Low | Zero-trust architecture; Keycloak auth; regular audits |

### Kill-Switch Rules

- Do NOT enter new city without 1 anchor client + local partner

- Do NOT launch new vertical without clear revenue owner

- Do NOT hire ahead of revenue — every new hire must be justified by growth metrics

- STOP hardware orders if sell-through rate drops below 60%

## 15. Equity & Governance

### 15.1 Proposed Equity Structure

| Stakeholder | Allocation | Notes |
| --- | --- | --- |
| Founder(s) | 55–60% | Controlling stake, hardware + vision |
| ESOP Pool | 10–12% | CTO, Payments PM, key hires (4-year vesting) |
| Seed/Angel Investors | 15–20% | This round (₦250M valuation basis) |
| Strategic Reserve | 10–15% | Future rounds, partnerships |

### 15.2 Corporate Holding Structure

PECH Group Holdings Ltd (Parent — Technology Company)
├── PECH Payments Ltd (Subsidiary — holds PSSP license)
├── PECH Terminal Services Ltd (Subsidiary — holds PTSP license, when justified)
└── Future subsidiaries as needed

The parent company (PECH Group Holdings Ltd) is a technology company that owns the platform, hardware IP, and brand. Payment and terminal licenses are held by dedicated subsidiaries to isolate regulatory risk and meet CBN single-purpose entity requirements.

### 15.3 Governance

| Position | Responsibility |
| --- | --- |
| Founder/CEO | Vision, hardware sourcing, partnerships, capital |
| CTO | Architecture authority, technical hiring, security |
| Advisory Board | Regulatory, finance, market access (3-5 advisors) |

### 15.4 Investor Protection

- Monthly financial reporting

- Board seat for lead investor (optional)

- Quarterly milestone reviews

- Anti-dilution provisions on next round

- Right of first refusal on Series A

## 16. Key Performance Indicators

### 16.1 Company-Level KPIs (Monthly Board Review)

| KPI | Month 6 | Month 12 | Month 18 | Month 24 |
| --- | --- | --- | --- | --- |
| Active Merchants (ERP) | 200 | 1,500 | 3,000 | 5,000 |
| IoT Devices Deployed | 50 | 300 | 800 | 1,500 |
| Markets Digitized | 1 | 3 | 5 | 8 |
| Spoke Stations Active | 2 | 10 | 20 | 30 |
| Monthly Revenue (₦) | 1.5M | 10.2M | 16.4M | 21.3M |
| Payment GMV (₦/month) | 20M | 150M | 500M | 1B+ |
| Team Size | 9 | 18 | 30 | 37 |
| Device Sell-Through Rate | 70% | 80% | 85% | 90% |
| Customer Churn (monthly) | <15% | <10% | <8% | <5% |
| System Uptime | 95% | 99% | 99.5% | 99.9% |
| PSSP License | — | — | Obtained | Active |

### 16.2 Role-Specific KPIs

| Role | Key Metrics |
| --- | --- |
| CTO | System uptime, deployment frequency, zero security incidents |
| Engineers | Features shipped/sprint, bug rate, code review quality |
| Market Ops | Merchants onboarded, active %, association satisfaction |
| Support | First-response time <2hrs, resolution <24hrs, churn reduction |
| Field Agents | 15-25 shops/day, >98% data accuracy, <5% rejections |

## 17. Use of Funds Summary

┌─────────────────────────────────────────────────────────────────┐
│           ₦250,000,000 CAPITAL DEPLOYMENT (24 MONTHS)           │
│                   PECH Group Holdings Ltd                        │
├─────────────────────────────────────────────────────────────────┤
│                                                                 │
│  HARDWARE — 25 SKUs (30.0%)  ₦75,000,000                      │
│  ├─ Commerce (POS, Tablets, Kiosks)   ₦22,000,000             │
│  ├─ IoT & Energy Devices              ₦13,000,000             │
│  ├─ Smart Water Controllers            ₦8,000,000             │
│  ├─ Smart Home (Switches, Cameras)     ₦6,000,000             │
│  ├─ Solar Products (Street Lights, Fans) ₦8,000,000           │
│  ├─ Learning Tablets + LED Displays    ₦6,000,000             │
│  ├─ Energy Storage Systems             ₦5,000,000             │
│  └─ SONCAP Certification (amortized)  ₦4,500,000             │
│  └─ Shipping + Import                 ₦2,500,000             │
│                                                                 │
│  PEOPLE (28.0%)              ₦70,000,000                       │
│  ├─ Engineering Team            ₦32,000,000                    │
│  ├─ Operations & Support        ₦18,000,000                    │
│  ├─ Field Agents                ₦10,000,000                    │
│  └─ Contractors (UI/UX etc)    ₦10,000,000                    │
│                                                                 │
│  TECHNOLOGY (11.2%)          ₦28,000,000                       │
│  ├─ Cloud Infrastructure (24mo)  ₦18,400,000                  │
│  └─ AI Tools & Subscriptions     ₦9,600,000                   │
│                                                                 │
│  OPERATIONS (8.0%)           ₦20,000,000                       │
│  ├─ Office Rent (24mo × ₦500K)  ₦12,000,000                  │
│  ├─ Equipment & Furniture        ₦3,000,000                   │
│  ├─ Utilities & Misc             ₦3,000,000                   │
│  └─ Product Display Shelves      ₦2,000,000                   │
│                                                                 │
│  CONTINGENCY & FX (7.2%)    ₦18,000,000                       │
│  └─ FX hedging, emergency, expanded product line buffer        │
│                                                                 │
│  MARKETING (6.0%)            ₦15,000,000                       │
│  ├─ Digital Marketing             ₦5,000,000                  │
│  ├─ Field Marketing & Events      ₦4,000,000                  │
│  ├─ Brand & Content               ₦3,000,000                  │
│  └─ Demo Stations & Workshops     ₦3,000,000                  │
│                                                                 │
│  LOGISTICS SETUP (4.8%)     ₦12,000,000                       │
│  ├─ Spoke Station Equipment       ₦8,000,000                  │
│  └─ Hub Setup & Branding          ₦4,000,000                  │
│                                                                 │
│  COMPLIANCE (4.8%)           ₦12,000,000                       │
│  ├─ SONCAP (3 shipments)          ₦4,500,000                  │
│  ├─ Legal Consulting (₦1M/yr)     ₦2,000,000                  │
│  ├─ Accountant Consulting (₦500K/yr) ₦1,000,000               │
│  ├─ Licenses & Permits             ₦2,500,000                 │
│  ├─ Trademark (1 class @ ₦100K)    ₦100,000                   │
│  └─ Buffer                          ₦1,900,000                │
│                                                                 │
│  [!] PSSP (AFTER MONTH 9 — FROM BUSINESS TRACTION)            │
│  ├─ PSSP: Capital + Escrow     ₦205,000,000                   │
│  └─ PCI DSS Certification       ₦5,000,000                    │
│                                                                 │
│  [!] FUTURE — WHEN JUSTIFIED                                   │
│  ├─ PTSP: Capital + Escrow     ₦201,000,000                   │
│  └─ MMO: Capital + Escrow      ₦4,001,000,000                 │
│                                                                 │
├─────────────────────────────────────────────────────────────────┤
│  TOTAL (FROM ₦250M): ₦250,000,000                             │
└─────────────────────────────────────────────────────────────────┘

## 18. Appendix

### A. Open-Source Technology Stack (Licensing Summary)

| Technology | License | Commercial Use | Role in PECH |
| --- | --- | --- | --- |
| AI & ML |  |  |  |
| Qwen2.5 (LLM) | Apache 2.0 | Yes — rebrand OK | Primary language model |
| Whisper (STT) | MIT | Yes | Speech-to-text |
| Piper TTS | MIT | Yes | Text-to-speech |
| PaddleOCR | Apache 2.0 | Yes | Invoice/document OCR |
| RT-DETR | Apache 2.0 | Yes | Object detection (replaces YOLOv8 AGPL) |
| Qwen2-VL | Apache 2.0 | Yes | Vision/image analysis |
| Ollama / vLLM | MIT / Apache 2.0 | Yes | Model serving |
| LangChain | MIT | Yes | RAG framework |
| Qdrant | Apache 2.0 | Yes | Vector database |
| XGBoost | Apache 2.0 | Yes | Fraud detection, credit scoring |
| MLflow | Apache 2.0 | Yes | ML experiment tracking |
| Apache Superset | Apache 2.0 | Yes | BI/Analytics (replaces Metabase AGPL) |
| Apache Airflow | Apache 2.0 | Yes | Workflow automation (replaces n8n) |
| Platforms |  |  |  |
| ThingsBoard CE | Apache 2.0 | Yes — rebrand OK | IoT platform base |
| ERPNext | MIT | Yes | ERP base (core is MIT) |
| Medusa | MIT | Yes | Marketplace/commerce |
| Apache Fineract | Apache 2.0 | Yes | Fintech core banking |
| Chatwoot | MIT | Yes | Customer support |
| Keycloak | Apache 2.0 | Yes | Authentication/identity |
| Apache APISIX | Apache 2.0 | Yes | API gateway (replaces Traefik) |
| Infrastructure |  |  |  |
| EMQX | Apache 2.0 | Yes | MQTT messaging |
| NanoMQ | MIT | Yes | Edge MQTT broker |
| NATS / Apache Kafka | Apache 2.0 | Yes | Event streaming |
| React | MIT | Yes | Web dashboards |
| Flutter | BSD | Yes | Mobile apps |
| k3s | Apache 2.0 | Yes | Lightweight Kubernetes |
| Leaflet | BSD-2 | Yes | Map visualization |

### B. Competitor Landscape

| Competitor | Strengths | Weakness vs PECH |
| --- | --- | --- |
| Tuya | Global scale, cheap devices | No African localization, WiFi-dependent |
| Paystack | Payment dominance | No ERP, no hardware, no IoT |
| TradeDepot | Distribution network | No IoT, no marketplace, no platform |
| Moniepoint | POS dominance | No ecosystem, no IoT, no marketplace |
| ThingsBoard | Open-source IoT | No commerce, no payments, no hardware |

### C. 15-Year Vertical Expansion Blueprint

15-Year Expansion Blueprint

| Phase | Years | Geography | Verticals Added | Key Milestones |
| --- | --- | --- | --- | --- |
| Foundation | 1–3 | Nigeria (Lagos, Abuja, Aba, Kano) | Commerce & POS, IoT & Smart Systems, Payments (via PSP), Spoke-Hub Logistics, Smart Home & Electrical, Smart Water Controllers, Learning Tablets, Energy Storage | ERP at 3,000+ merchants, 800+ IoT devices, own PSSP/PTSP licenses obtained |
| Expansion | 4–6 | West Africa (Ghana, Ivory Coast, Kenya) | Energy (Solar/Mini-Grid), Agriculture (Smart Farming), Water (Utility-Scale), Smart Cities (Estate Mgmt), Own PSSP/PTSP/MMO | Multi-country operations, 10+ verticals, installer ecosystem launched |
| Multi-Vertical | 7–10 | 8–10 African countries | Mobility & Fleet Tracking, Telecom Integration, Government & Utility Partnerships, Insurance (InsurTech), Certified Installer Network | Cross-border trade platform, government contracts, 12+ verticals |
| Pan-African Dominance | 11–15 | 15+ countries | Sovereign Cloud Infrastructure, Embedded Fintech (Loans/Credit), Digital Identity, Cross-Border Trade Platform, Developer Platform & Open API Ecosystem | Pan-African infrastructure OS, developer marketplace, data services |

Note: Revenue projections for years 4-15 are not included as they depend on market conditions, regulatory environments, and capital availability at each phase. PECH will publish updated projections at the end of each phase based on actual performance data.

### D. Contact

PECH Group Holdings Ltd Lagos, Nigeria Pechenergysolutions@gmail.com | pechgroupholdings.tech

This document is confidential and intended solely for the use of prospective investors and strategic partners of PECH Group Holdings Ltd. Unauthorized distribution is prohibited.

PECH Group Holdings Ltd  |  Lagos, Nigeria  |  pechgroupholdings.tech